Week 8 Work Log: Developing a Testing and Quality Assurance (QA) Plan

Complete this worksheet as a team during or after the Week 8 workshop. Add more rows if needed.

| Group | Forecasting 4 | Workshop | Thursday 3:30pm – 5:30pm |
| --- | --- | --- | --- |
| Project title | Forecasting Model Development: AI Powered Energy Prediction | Date | 02/10/2026 |
| Client | ARC Research Hub for Integrated Energy Storage Solutions | Members present | Yaqiao, Bhumika, Vidhi |

Activity 1  Features, quality metrics and expectations

List the features your project is actually building, then say what "working well" means for each one. An expectation is only useful if it can be measured - "search should be fast" is an opinion, "search returns results in under 2 seconds with 1000 records" is a target you can test against. Choose the testing type from the list covered in the lecture.

| Feature / module | Expectation - what "good" looks like | Quality metric | Target value | Testing type | How it will be verified |
| --- | --- | --- | --- | --- | --- |
| F1 – Data cleaning pipeline (PJM Hourly Energy Consumption) | The cleaned file has one row per hour, in time order, with no duplicates, no gaps and no invalid values. | - Duplicate timestamps; - missing hours; - negative / null values; - row count vs. expected hourly count | - 0 duplicates, 0 missing hours, 0 nulls; - row count = expected number of hours between first and last timestamp | Unit testing (white-box) | - Assertion checks at the end of data_cleaning.ipynb; - results logged in /docs/results/ |
| F2 – Feature engineering (time features + Lag_1h, Lag_24h, Lag_168h) | Every feature uses only past data, so no future information leaks into the model. | - Number of features that use future values; - lag values match the shifted load column | - 0 leaking features; - 100% of 20 randomly sampled rows match manual lag calculation | Unit testing (white-box) | - Spot-check script compares Lag_24h at time t with load at t-24h; - code review by second member |
| F3 – XGBoost baseline | Gives stable, repeatable results on an unseen, later time period. | - MAE, RMSE, MAPE on the chronological test set; - difference between two runs with the same seed | MAPE <= 1.10% on PJM (current 1.066%); - re-run difference < 1% | Unit testing + regression testing | - Re-run notebook with fixed random seed; - compare against recorded baseline metrics |
| F4 – LSTM model | More accurate than the baseline and trainable within free Colab limits. | - MAE, RMSE, MAPE; - training time on Colab T4 GPU; - checkpoint saved | - MAPE <= 0.80% (current 0.783%); - training <= 30 min (NFR3); - checkpoint file exists after training | Performance testing + regression testing | - Time the training cell; - confirm checkpoint reloads and reproduces the same test metrics |
| F5 – Hybrid model (error- reciprocal weighting) | Combines both models correctly and is at least as accurate as the best single model. | - Weights sum to 1; - weights calculated from validation error only (not test); - hybrid MAE vs. single-model MAE | - weights sum = 1.000; - hybrid MAE <= LSTM MAE (current 241.58 vs. 245.66 MW) | Integration testing | - check the weight calculation well uses the validation split; - compare evaluation matrix rows side by side |
| F6 – Interpretability + plain-English summary (SHAP, LIME) | Explanations are generated quickly and a non-technical reader can understand the main drivers of a forecast. | - SHAP plot generation time; - number of predictions explained; - reader comprehension | - <= 3 s per SHAP plot (NFR4); - >= 3 predictions explained per model; - reader answers 3/3 comprehension questions correctly | Performance testing + usability testing | - time plot generation in Colab; - give the one-page summary to a reader outside the technical work with 3 short questions |

QA and QC approaches for your project

|  | Approach or technique you will use | Why it suits your project | Tool or resource needed |
| --- | --- | --- | --- |
| QA (preventive) | Peer code review: every notebook change is reviewed by the other active member before it is merged into the main branch on GitHub | Only two active developers, so a second pair of eyes is the cheapest way to catch data leakage and logic errors before they reach the results | GitHub (pull requests / commit comments) |
| QA (preventive) | Reproducibility controls: fixed random seeds, a requirements.txt with library versions, and a strict chronological train / validation / test split rule. | ML results can change between runs and Colab sessions; Fixing these up front prevents results we cannot repeat in the final report | Python, requirements.txt, Google Colab |
| QC (detective) | Automated assertion checks in each notebook (data shape, duplicates, missing values, weights sum to 1, no NaN in predictions). | Detects broken data or pipeline errors immediately after each run, instead of finding them later in the metrics. | Python assert statements, pandas |
| QC (detective) | Metric regression check and residual analysis: after any change, compare MAE / RMSE / MAPE with the recorded baseline and plot residuals for peak and anomaly periods. | Shows whether a change made the models worse, and where (e.g., evening peaks or unusual days) the models fail. | Evaluation matrix in /docs/results/, Matplotlib |

| Non-functional expectations you must still meet (performance, security, usability) | Performance: LSTM training <= 30 min on Colab T4 (NFR3); SHAP plot <= 3s per prediction (NFR4). Usability: all charts have titles, axis labels and units (MW); the summary avoids technical terms (NFR 6). Reproducibility: the main notebook runs top-to-bottom in a fresh Colab session from the GitHub repo without manual fixes. Security / data: only public datasets are used; no confidential market data and no API keys or passwords committed to GitHub |
| --- | --- |
| Definition of done - when does the team agree a feature is finished? | A feature is done when: (1) The is committed to GitHub (2) it runs top-to-bottom in a fresh Colab session (3) its assertion checks pass (4) its metrics or outputs are saved in /docs/results/ (5) the other active member has reviewed it (6) it is recorded in the weekly worklog |

Activity 2  Testing and QA plan

Turn the metrics above into a plan someone else could execute. Name a real person for each role and real dates for each phase - a schedule with no owner is a wish list. Keep the scope to what your team can genuinely test in the weeks remaining, and say plainly what is out of scope.

| Testing objective | In scope | Out of scope | Testing type | Resources | Roles |
| --- | --- | --- | --- | --- | --- |
| Verify data quality of the cleaned dataset | Cleaned PJM dataset (PJME_hourly_cleaned.csv) | Household Electric Power Consumption and Real-E (removed from scope with tutor approval, 1 Oct); Real-time grid data; Confidential market data | Unit testing | Pandas, Colab | Yaqiao (tester), Bhumika (reviewer) |
| Confirm no data leakage in features and splits | Time and lag features; Chronological train / validation / test split | New feature types (e.g. weather) not in the current pipeline | Unit testing, code review | Python GitHub | Bhumika (tester), Yaqiao (reviewer) |
| Verify model accuracy and stability | XGBoost, LSTM and hybrid on the PJM test period; MAE, RMSE, MAPE | Extensive hyperparameter search; Forecast horizons other than the current one-step-ahead setup | Regression testing, integration testing | Colab T4 GPU, evaluation matrix | Yaqiao (LSTM, hybrid), Bhumika (XGBoost) |
| Check robustness across different conditions within PJM | Error by season, weekday vs. weekend, and peak vs. off-peak hours on the PJM test period; Largest-error days (anomalies / edge cases) | Testing on other datasets (cross-dataset validation removed from scope) | System testing | Evaluation matrix, residual plots, Colab | Bhumika |
| Check interpretability is usable | SHAP / LIME for 3 predictions per model; On-page plain-English summary | Interactive dashboard (scope creep, risk R4) | Performance testing, usability testing | SHAP, LIME summary template | Yaqiao (author), [Vidhi as non-technical test reader, if confirmed after meeting] |

Test schedule

| Task name | Start | Finish | Effort | Comments |
| --- | --- | --- | --- | --- |
| Test planning | 01/10/2026 | 02/10/2026 | 3 h | This QA plan (Week 8 worklog) |
| Review requirements documents | 02/10/2026 | 04/10/2026 | 2 h | Re-read FRs/NFRs from Week 2 and Week 5 traceability matrix; Map each to a test |
| Create test basis / test cases | 05/10/2026 | 08/10/2026 | 4 h | Write assertion checks and test cases for F1-F6 |
| Unit and integration testing | 08/10/2026 | 13/10/2026 | 6 h | Run checks on cleaning, features and hybrid weighting |
| System testing | 12/10/2026 | 16/10/2026 | 5 h | Run full pipeline end-to-end in a fresh Colab session; Error breakdown by season and peak hours |
| Performance and usability testing | 14/10/2026 | 18/10/2026 | 4 h | Time LSTM training and SHAP plots; Test summary with a non-technical reader |
| Regression testing | 19/10/2026 | 22/10/2026 | 3 h | Re-run all metrics after final changes; Compare with recorded results |
| Resolution of final defects | 20/10/2026 | 25/10/2026 | 4 h | Fix remaining issues before final documentation (Week 11) |

Contribution register

Every member completes at least one row in their own words. Mark each task M for management (planning, client contact, minutes, scheduling, risk, document control) or T for technical (research, requirements drafting, design, prototyping, testing, tooling). Evidence must be something the tutor can open; rows without evidence do not count.

| Member name | Task / activity completed this week | Type (M / T) | Evidence (link, file, commit, minutes) | Time spent (hrs) |
| --- | --- | --- | --- | --- |
| Yaqiao Chi | - Drafted the Week 8 Testing and QA plan (features F1-F6, quality metrics, test schedule). - Restructured the Jira board (6-7 Oct): aligned sprints with teaching weeks, corrected outdated items and added QA tasks from this plan. - Started implementing the QA plan (7-8 Oct, before this log was submitted): - LSTM hyperparameter tuning on a chronological validation set (units 32/64/128; window 24/48/168). Selected 64 units and a 168-hour window. - Evaluated dropout (0.2). It increased validation MAE by about 100 MW, so it was not kept; early stopping was retained. - Fixed a data-leakage issue in the hybrid model: weights are now calculated from validation error instead of test error (LSTM 0.600, XGBoost 0.400). - Retrained and re-evaluated: LSTM test MAE 217.78 MW (MAPE 0.699%); hybrid 215.41 MW (MAPE 0.684%). LSTM training took 5.4 minutes (NFR3 met). - Re-ran SHAP/LIME, added an aggregated LIME temporal attribution chart (20 test predictions) and rewrote the Interpretability Results. - Logged a defect: the notebook requires the data file to be re-uploaded in a new runtime (linked to IF$T-85). | M & T | Google Colab notebook “forecasting4”: https://github.com/Yaqiao-chi-helen/Forecasting-team4/blob/main/notebooks/Model_Development_XGBoost_LSTM.ipynb sections “Hyperparameter Tuning”, “Hybrid Weights (validation-based)” and “Temporal Attribution” Jira Board: https://ict30016.atlassian.net/jira/software/projects/IF4T/boards/3/backlog | 10 h |
| Bhumika Sharma | Developed the testing and QA plan for the PJM forecasting pipeline. Defined checks for feature-engineering data leakage, chronological train/validation/test splits, XGBoost baseline accuracy and model stability, and robustness testing across seasons, weekdays/weekends, peak/off-peak periods and anomalous days. Also reviewed the project's testing scope and quality metrics following the decision to use PJM as the only dataset. | M & T | Testing and QA Plan; Google Colab/Jira testing tasks | 5 hours |
| Vidhi Patel | Re-engaged with the project and reviewed the team's current progress, including the implemented XGBoost, LSTM and hybrid forecasting models and SHAP/LIME interpretability work. Reviewed the Week 8 Testing and Quality Assurance Plan to understand the project's testing objectives, quality metrics, testing approaches and remaining deliverables. Participated in team communication/meeting to understand the updated project scope and discuss my responsibilities for the upcoming testing phase. Prepared notes on the current project status and the tasks I will contribute to during the next stage. | M |  |  |
| Marwa Aldhafeeri |  | N / A | N / A | N / A |

Agreed actions for the coming week

| Owner | Action to complete before next workshop | Due date |
| --- | --- | --- |
| Yaqiao | Load data from GitHub instead of manual upload (IF4T-85); Add assertion checks (IF4T-81) | 15 Oct |
| Yaqiao | Write the plain-English summary (IF4T-89) | 18 Oct |
| Bhumika | Lag feature leakage spot-check (IF4T-82) Fix random seeds + requirements.txt (IF4T-84) | 16-18 Oct |
| Bhumika | Error breakdown by season / weekday / peak, and top-5 error days (IF4T-88) | 18 Oct |
| Vidhi | Fresh Colab end-to-end run to test reproducibility (IF4T-86) | 17 Oct |

Anything blocking the team, or any contribution imbalance the tutor should know about?

Update on Vidhi and Marwa. On 1 October, Yaqiao and Bhumika discussed the two inactive members with Mr Fusen. On his advice, Bhumika posted a message in the team chat asking both members to confirm by Monday 5 October whether they will take part and inviting them to an online meeting to discuss scope and roles.

Vidhi replied on the same day. She apologised, said she wants to participate, shared her availability for a meeting, and said she will attend the Thursday workshop. Because the project is now well into the technical stages, we will hold the meeting first so she can understand the current work, rather than assigning tasks without context. Her contribution will be recorded from the week she starts work; her contribution for Weeks3—7 and the Innovation Concept assignment remains as previously reported (0%).

Marwa replied on the same day too, but she did not provide a specific time. If she still hasn’t responded by 5 October, we will let the tutor know and continue planning the remaining work for the active members.

The project itself is on track: LSTM, hybrid model and SHAP / LIME analysis are complete, and Weeks 9-10 will focus on testing, anomaly / edge-case analysis and the plain-English summary.

Scope change. Because only two members have been active, Mr Fusen confirmed on 1 October that the team only needs to use one dataset (PJM). Cleaning and validation on the Household Electric Power Consumption and Real-E datasets have been removed from scope. To still check how well the models generalise, we will test performance across different periods and conditions within the PJM data (seasons, weekends, peak hours and unusual days).

Update (8 Oct): Implementation of the QA plan has started. LSTM tuning and the dropout check were completed using validation data only, and the hybrid weighting was corrected to avoid using test data. All three models now meet the targets in Activity 1 (F3-F5). The remaining QA tasks are tracked in Jira Sprint 4.