Week 4 Work Log: Risk and Uncertainty

Complete this worksheet as a team during or after the Week 4 workshop. Add more rows if needed.

| Group | Forecasting 4 | Workshop | Thursday 3:30 – 5:30pm |
| --- | --- | --- | --- |
| Project title | AI-Powered Energy Prediction: Forecasting Model Development | Date | 31/08/2026 |
| Client | ARC Research Hub for Integrated Energy Storage Solutions | Members present | Yaqiao, Vidhi, Marwa, Bhumika |

Activity 1 Scope of uncertainty and risk in your innovation process

Answer as a team, about your own project. Keep answers concrete - "things might go wrong" is not an answer..

| What are we trying to achieve? | We are building a prototype forecasting platform that compares LSTM and XGBoost models, with built-in interpretability features. The goal is to help grid operators make better decisions using accurate and explainable load forecasts. |
| --- | --- |
| What could affect us while seeking to achieve this? | - Team members missing workshops (Bhumika was absent Weeks 2-4). - Uneven contribution levels (some members not completing research tasks on time). - Technical challenges with LSTM implementation (team has foundational but not export ML knowledge). - Google Colab session timeouts interrupting long training runs. - Dataset inconsistencies across three public datasets (different formats, time zones, feature sets). |
| Which of those factors are most important? | - LSTM skill gap: this is on the critical path and delays the whole project. - Team coordination: missing workshops and uneven contribution have caused work to pile up. - Colab resource limits: could interrupt training and waste time. |
| What could we do about them, and have we done what’s appropriate? | - Scheduled a catch-up meeting for Bhumika (but she was absent). - Started using Jira to track tasks and make progress visible. - Sharing LSTM tutorials in the group chat. - Using GitHub for version control and Colab for training with early stopping and checkpoints. - Plan to have a conversation with Marwa about group work. |
| Did it work, or do we need to adapt? | We have rescheduled the catch-up meeting to take place during the weekly workshop. Jira is set up. GitHub and Colab are working. The conversation with Marwa still needs to happen. We need to make sure Bhumika is fully up to speed after her return. |
| What did we learn? | Clear task ownership and regular check-ins are essential. We need to set small, mandatory deliverables early to avoid work piling up. Without visible progress tracking, it’s hard to know who is falling behind until it’s too late. |

Activity 2  Risk uncertainty plot

Uncertainty is not knowing what will happen; risk is the consequence if it does. Rate each element, then write each item number into the grid cell that matches. Incremental and radical elements should not land in the same place

| # | Project element / initiative | Type (incremental / radical) | Level of uncertainty (L/M/H) | Potential risk (L/M/H) |
| --- | --- | --- | --- | --- |
| 1 | LSTM model implementation | Incremental | H | H |
| 2 | Team member attendance/participation | Incremental | M | H |
| 3 | Cross-dataset preprocessing pipeline | Incremental | M | M |
| 4 | Google Colab training stability | Incremental | M | M |
| 5 | Interpretability integration (SHAP/LIME) | Incremental | L | L |

Activity 3  SWOT analysis for risk identification

Complete all four quadrants, but mine the Weaknesses and Threats boxes for risks - every item you write there should turn into a numbered risk in Activity 4 or be consciously discarded.

| Strengths (internal, helpful) | Weaknesses (internal, harmful) → risk source |
| --- | --- |
| - Team has complementary skills (Python, data, ML, documentation). - GitHub and Jira are set up. - Weekly worklogs provide a record of progress. - Facilitator feedback is available weekly. | - Some team members have been absent from workshops. - Uneven contribution levels across members. - Foundational but not expert ML knowledge. - Work has piled up due to lack of early checkpoints. - Procrastination risk without clear deadlines. |
| Opportunities (external, helpful) | Threats (external, harmful) → risk source |
| - Public datasets are available (Panama, PJM, Real-E). - Google Colab provides free GPU access. - Existing literature on LSTM and XGBoost provides clear guidance. - Agile methodology allows us to adapt. | - Google Colab session timeouts. - Dataset inconsistencies across sources. - Team member availability may remain unstable. - Risk of scope creep if we spend too long on dashboards. |

Activity 4  Project risk log

Transfer the risks and strategies above into the log, with an owner and a review date for each. This log is a living document - bring it to every remaining workshop and update the status column.

| ID | Risk description | Category | Like. | Impact | Rating / priority | Owner | Review date & status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Skill gap in LSTM/GRU implementation → delays on critical path | Technical | H | H | Critical | Yaqiao | Week 5 – In Progress |
| R2 | Data inconsistency across three public datasets → wasted time on wrangling | Data | M | H | High | Vidhi | Week 5 – Mitigation planned |
| R3 | Google Colab session timeout → training interrupted | Technical | M | M | Medium | All | Week 5 – Checkpoints in place |
| R4 | Scope creep (fancy dashboards instead of core models) | Management | H | M | High | Yaqiao | Week 5 – Agile backlog in use |
| R5 | Procrastination/uneven contribution → missed weekly deadlines | Team | H | H | High | Marwa, Bhumika | Week 5 – Conversation planned |
| R6 | Bhumika’s absence Weeks 2-4 → knowledge gap on return | Team | M | M | Medium | Yaqiao | Week 5 – Catch-up meeting scheduled |

Contribution register

Every member completes at least one row in their own words. Mark each task M for management (planning, client contact, minutes, scheduling, risk, document control) or T for technical (research, requirements drafting, design, prototyping, testing, tooling). Evidence must be something the tutor can open; rows without evidence do not count.

| Member name | Task / activity completed this week | Type (M / T) | Evidence (link, file, commit, minutes) | Time spent (hrs) |
| --- | --- | --- | --- | --- |
| Yaqiao Chi | Led risk identification and SWOT analysis; drafted Week 4 worklog; updated GitHub repo with project structure; set up Jira board and created sprint tasks | M & T | Week 4 worklog submitted; GitHub repo: https://github.com/Yaqiao-chi-helen/Forecasting-team4; Jira board: https://ict30016.atlassian.net/jira/software/projects/IF4T/boards/3 | 5 h |
| SVidhi Jaydipkumar Patel | Confirmed data preprocessing progress for Panama dataset | T | Shared progress update in group chat | 2 h |
| Marwa Aldhafeeri | Contributed to the assignment 1 literature review on XGBoost/tree-based models | T |  | 2.0 h |
| Bhumika Sharma | Could not contribute towards anything due to lack of resources and not having any access to Swin Cloud/Canvas. | M |  | N/A |

Agreed actions for the coming week

| Owner | Action to complete before next workshop | Due date |
| --- | --- | --- |
| Yaqiao | Complete LSTM environment setup (TensorFlow, Colab) and start baseline LSTM model | Next Thursday’s workshop |
| Vidhi | Finalise feature engineering pipeline on Panama dataset | Next Thursday’s workshop |
| Marwa | Complete XGBoost baseline model training and share initial results | Next Thursday’s workshop |
| Bhumika | Attend the workshop and catch up with the group’s progress. | Next Thursday’s workshop |
| All | Take 15-20 minutes meeting during the Thursday workshop to align on progress | Next Thursday’s workshop |

Anything blocking the team, or any contribution imbalance the tutor should know about?

We have two issues to report:

- Bhumika’s continued absence. Bhumika missed Weeks 2, 3, and 4 workshops. She was unable to attend the catch-up meeting scheduled for Week 4 due to visa issues preventing her from accessing Canvas and Swinburne Cloud. She has indicated she will attend the Week 5 workshop, but this remains unconfirmed. If she does not return in Week 5, the remaining team members will need to adjust worklog distribution to ensure project continuity.

- Marwa’s contribution has improved. Marwa had low participation in Weeks 2-3. After a discussion with the facilitator and the team during the Week 4 workshop, she has committed to checking group messages and emails regularly. We expect her contribution to increase moving forward.

We will continue to monitor attendance and contribution, and adjust as needed.